## Sheet1
Maintenace log
Area/Location | Issue | Date Reported | Action | Who is Responsible? | Date of Chase (if applicable) | Date Resolved | notes
Sugar Hill | 2 toilet seats vandalised | 2021-11-01 | clerk to appoint contractor | P&M | 2021-12-01 | 2022-03-01
Southfield Terrace | Escape of Water | 2021-12-01 | Reported to BMDC | BMDC | 2022-02-01 |  | REF:CR419651-1004874032
Newtown | Old shed left by previous plot holder. Damaged and needs removing plot 4a/4b | 2021-10-01 | Contractor appointed | P&M | 2022-01-01
Newtown | Erect fence behind 4a. Boundary with footpath | 2021-10-01 | Contractor appointed | P&M | 2022-01-01
Newtown | Mature trees on Stockinger lane (alley way) overhanging plots. Need cutting back. Plot 1-5 | 2021-10-01 | Contractor appointed | P&M | 2022-01-01 | Work completed March 2022
Newtown | Plot 13 - 2 large dangerous sheds left by outgoing tenant need to be removed from the plot. | 2021-10-01 | Contractor appointed | P&M | 2022-01-01 | Work completed March 2022
Newtown | Overgrown trees/bushes/weeds need cutting back to fence line to expose the plot for the new plot holder. Plot 13 | 2021-10-01 | Contractor appointed | P&M | 2022-01-01 | Work completed March 2022
Silsden Road | Cuttings dumped on plot 8a | 2021-11-01 |  | P&M
Lower Stamphill | Plot 10. Damaged fence post needs securing in place | 2022-08-01 |  | P&M
Lower Stamphill | Plot 5a – needs a total overhaul | 2021-12-01 |  | P&M |  | Work complete March 2022
Stamphill | Rear fencing (Nature reserve)plots 29-34 | 2021-08-01 | Site visit required to agree extent of scheme | P&M
Stamphill | Plot 26 needs new fence OR clearance of debris | 2021-08-01 |  | P&M
Sildsen Road Recreation Field | Broken drain needs investigating and replacement | 2021-08-01 | Contractor appointed | Approved by Council
Old School Hub | Sensor light for outside steps | 2021-11-01 | Replace bulb with brighter one | P&M
Pavilion | Burco water heater | 2021-11-01 | Contractor appointed | P&M
Mem Hall recreation park | Man hole cover missing | 2022-01-01 | Reported to Bradford. Temporary cover in place | P&M
Pavilion | Guttering end cap missing. Sealant along joint required | 2022-01-01 |  | P&M
Skipton Road/Heathness Road | Escape of water. Blocked drain. Leaves on footpath and highway | 2021-12-01 | Clerk to report to BDMC | P&M | 2022-03-01
Pavilion Disabled toilet | Locked vandalised | 2022-02-01 | fit temporary bolt
Stamp Hill | Plot 29&30. Overhanging trees need pruning | 2022-02-01 | to look at during the inspection | P&M
Old School Hub | Steps need white lines painting on | 2022-03-01 |  | P&M
Old School Hub | Gardening/weeding along stoned area behind Hub | 2022-03-01 |  | P&M