## Sheet1
Maintenace log
Area/Location | Issue | Date Reported | Action | Who is Responsible? | Date of Chase (if applicable) | Date Resolved | notes
Southfield Terrace | Escape of Water | 2021-12-01 | Reported to BMDC | BMDC | 2022-06-01 |  | REF:CR419651-1004874032
Silsden Road | Cuttings dumped on plot 8a | 2021-11-01 |  | P&M |  | 2022-06-01
Lower Stamphill | Plot 10. Damaged fence post needs securing in place | 2022-08-01 |  | P&M
Stamphill | Rear fencing (Nature reserve)plots 29-34 | 2021-08-01 | Site visit required to agree extent of scheme | P&M |  |  | awaiting quotes
Stamphill | Plot 26 needs clearance of debris | 2021-08-01 |  | P&M |  | 2022-07-01
Sildsen Road Recreation Field | Broken drain needs investigating and replacement | 2021-08-01 | Contractor appointed | Approved by Council |  | 2022-06-01
Old School Hub | Sensor light for outside steps | 2021-11-01 | Replace bulb with brighter one | P&M |  |  | contractor appointed
Pavilion | Burco water heater | 2021-11-01 | Contractor appointed | P&M | 2022-06-01
Mem Hall recreation park | Man hole cover missing | 2022-01-01 | Reported to Bradford. Temporary cover in place | P&M | 2022-06-01 |  | Chased by the Clerk with additional photos
Skipton Road/Heathness Road | Escape of water. Blocked drain. Leaves on footpath and highway | 2021-12-01 | Clerk to report to BDMC | P&M | 2022-04-01 | 2022-06-01
Pavilion Disabled toilet | Locked vandalised | 2022-02-01 | fit temporary bolt |  |  | 2022-03-01
Stamp Hill | Plot 29&30. Overhanging trees need pruning | 2022-02-01 | to look at during the inspection | P&M |  | 2022-06-01 | Trees assessed by Arborist in May 2022. Advice to leave alone.
Nature Reserve | Removal of deceased Ash tree. Severing of Ivy from large trees at entrance | 2022-05-01 |  | Approved by Full Council May 2022 |  | 2022-06-01
Old School Hub | Steps need white lines painting on | 2022-03-01 |  | P&M |  |  | contractor appointed
Old School Hub | Gardening/weeding along stoned area behind Hub and parking space | 2022-03-01 |  | P&M |  | 2022-05-01
Public Toilets | Pavilion toilets vandalised April , May & June 2022 | 2022-06-01 |  |  |  |  | Currently closed
Lower Stamphill | 6 large tractor Tyres | 2022-03-01 |  | P&M |  |  | Clerk has tried 4 private waste firms and BMDC. Noone will remove and dispose of these tyres
Pathway near MUGA | Broken flags | 2022-04-01 |  | BMDC |  |  | Awaiting report from officers