## Sheet1
Maintenace log
Area/Location | Issue | Date Reported | Action | Who is Responsible? | Date of Chase (if applicable) | Date Resolved | notes
Southfield Terrace | Escape of Water | 2021-12-01 | Reported to BMDC | BMDC | 2022-06-01 |  | REF:CR419651-1004874032
Lower Stamphill | Plot 10. Damaged fence post needs securing in place | 2022-08-01 |  | P&M
Stamphill | Rear fencing (Nature reserve)plots 29-34 | 2021-08-01 | Site visit required to agree extent of scheme | P&M |  |  | awaiting quotes
Mem Hall recreation park | Man hole cover missing | 2022-01-01 | Reported to Bradford. Temporary cover in place | P&M | 2022-06-01 |  | Chased by the Clerk with additional photos
Public Toilets | Sugar Hill Toilets. Sink pipework damaged | 2022-11-01 |  | P&M
Lower Stamphill | 6 large tractor Tyres | 2022-03-01 |  | P&M |  |  | Clerk has tried 4 private waste firms and BMDC. Noone will remove and dispose of these tyres
Pathway near MUGA | Broken flags | 2022-04-01 |  | BMDC |  |  | Not sufficient trip hazard to warant a repair
Memorial Hall | put up plaque | 2022-07-01 |  | P&M |  | 2022-09-01 | contractor appointed
village wide | grafiti | 2022-07-01
LSH | Rabbit Fence along northern boundary | 2022-09-01 |  | P&M |  | 2022-09-01
Sugar Hill toilets | Gents toilet seat | 2022-08-01 |  | P&M
Hen Pen Gardens | Overgrown foliage close to properties | 2022-09-01 |  | P&M |  |  | Garden Friends will prune in Autumn
Amenity field (Footbal Pitch) | Request to cut overhanging branches back | 2022-08-01 |  | P&M |  | 2022-09-01
MUGA | Minor repairs identified in the ROSPA inspection | 2022-09-01 |  | P&M